## Slide 1: IT 3223
Project Planning

## Slide 2: Why have a project plan ?
The key to a successful project is in the planning. This can save you
Time
Money
Other problems.
The "Project plan" is a set of living documents that can be expected to change over the life of the project.

## Slide 3: project planning
The project plan answers the who, what, where, why, how and when of the project.
The purpose of a project plan is to guide the execution and control project phases.

## Slide 4: Project Audience
Audience for the project plan
  Stakeholders such as
    Business management
    Project team
    Users

## Slide 5: What is in project planning?
Project Charter: A general overview of the project describing the project’s reasons, goals, objectives, constraints, stakeholders, among other aspects.
Statement of Work: Defines the project’s scope, schedule, deliverables, milestones, and tasks.
Work Breakdown Structure: Breakdown of the project scope into the project phases, subprojects, deliverables, and work packages that lead to your final deliverable.
Project Plan: Documentation of scope management, quality management, risk assessment, resource management, stakeholder management, schedule management and the change management plan.

## Slide 6: Also in a project plan
  A resource list
    Team with skillsets
    Materials ( i.e., hardware, software, network, infrastructure )
  A project schedule
    Timeline and milestones
  Budget
  Risks and assumptions

## Slide 7: Project Manager
It is the Project Manager’s job to manage achievement of needed deliverables.
Deliverables are used to determine whether or not the project is on track during execution

## Slide 8: The project scope statement
Most important statement in the project plan.
Properly done, the scope statement decreases the chances of miscommunication.
In a way, it is a contract between the project manager and sponsor - one that can only be changed with sponsor approval.

## Slide 9: The project scope statement, continued
The scope statement should include:
Business needs
Project objectives
Benefits of project completion
Deliverables to be included or excluded from the project

## Slide 10: Project team must determine “what” and “who”
Determine stakeholders, their role and how projects impacts them
Interview stakeholders to determine needs.
List needs and prioritize them. Verify need vs nice to have
Create a set measurable goals.

## Slide 11: Statement of work
Introduction
  What are the business needs ?
  Who are the involved parties ?
What Is the Purpose of the Project?
  Why initiate this project?
  What is the purpose?
  What are the deliverables & objectives ?
  Often supported by return on investment - return of the project investment divided by the cost of the investment

## Slide 12: Statement of work, Continued
Scope of Work
  What work MUST to be done in the project?
  Should include deliverables to be included and excluded from the project
  What hardware and software are necessary?
  What process will be used to complete the work?
  What are the Project Outcomes?
  What are the general time estimates/deadlines?
  What general steps are to be taken?
Where Will the Work Be Done?
  Team location(s).
    Central facility or remote workers?

## Slide 13: Work Breakdown Structure
“A work breakdown structure defines all the things a project needs to accomplish, organized into multiple levels, and displayed graphically.”
https://www.workamajig.com/blog/guide-to-work-breakdown-structures-wbs

## Slide 14: Work breakdown
Develop a work breakdown structure (WBS) to identify activities and tasks to complete the project
The Work Breakdown Structure (WBS) provides a structural view into the project
WBS breaks down work packages where a work package contains between 8 and 80 hours of work to complete

## Slide 15: How to Create a Work Breakdown Structure
Determine the major deliverables or products to be produced.
Divide each of these major deliverables into its component deliverables in the same manner.
Divide each of these component deliverables into work pieces.

## Slide 16: Project Deliverables
Create a list of items needed for the project to meet those goals.
Specify when and how to deliver each item.
Add the deliverables to the project plan with an estimated delivery date.

## Slide 17: Smart principle
To ensure goals are clear and reachable, verify that they are:
Specific (simple, sensible, significant).
Measurable (meaningful, motivating).
Achievable (agreed, attainable).
Relevant (reasonable, realistic and resourced, results-based).
Time bound (time-based, time limited, time/cost limited, timely, time-sensitive).

## Slide 18: Roles and Responsibilities
Who are the stakeholders?
What are their needs?
  One way to find this is by conducting stakeholder interviews
Have a list of needs then prioritize them.
Create a set measurable goals.
Review goals against the SMART principle.
Once the project plan is complete, deliver its contents to key stakeholders.

## Slide 19: Human Resource Planning
Identify, by name, number, type of people, their roles and responsibilities to carry out the project.
Put the start dates, the duration and the method you will use for obtaining them.

## Slide 20: Resources : Includes materials and staff
What infrastructure changes are required?
What hardware is needed?
What software is needed?
What skillsets are needed to review, estimate and implement?
Are skillsets available in house or do contractors need to be hired?
Are skillsets co-located? If not, can they work remotely?
Do temporary arrangements need to be made for them on location?

## Slide 21: Project schedule
Use the work breakdown structure (WBS) to identify activities and tasks to complete the project:
  What resources are needed to complete each task
  Consider how much time each resource can devote to this each task
  Estimate how many hours it will take to complete each task
  Estimate cost of each task
More: https://www.projectmanagementdocs.com/template/project-planning/work-breakdown-structure/#ixzz6qohuLSZa

## Slide 22: Ready for Project Plan?
Once as much of the information is obtained and confirmed, you are ready to put all of the tasks, durations and the resources needed to complete each task into the plan document.

## Slide 23: Begin the project schedule
Define for project as per scope defined
  Activities/Tasks required
  Deliverables
  Milestones
Schedule the project constraints
  Planned start date
  The amount of effort (hours or days) required for completing each task
  The resources needed to complete the task
  An accurate delivery date for each task.
  Planned finish date

## Slide 24: Project Schedule Continued
Considering the deliverables/tasks that need to performed. Determine the following:
Input all of the tasks, durations and the resources needed to complete each task into a calendar
Determine cost-by-time period for your budget
Determine critical path

## Slide 25: Critical path
Determine the important deadlines to deliver a project on time
Consider the longest distance between the start and the finish
  Include all the tasks and their duration in the project plan
Calculate the Critical Path
  Review tasks needed to complete the project.
  Review Task Duration to ensure they are reasonable
  Review Task Dependencies
    What task cannot start until another one has been finished?
  What are the milestones in the project?
    Based on dependencies, can the milestones be met?

## Slide 26: Determine budget
Consider costs:
  Personnel per deliverable required
  Infrastructure
    Construction
    Hardware
    Software
    Network
Business often has control of funds for project
  Negotiation may be needed for real world costs
  This may be where a go-no-go decision is made
    Does return on investment exceeds cost?

## Slide 27: A common problem
Sponsor imposing a delivery deadline that is not realistic based on your estimates.
The options you have in this situation are:
Renegotiate the deadline (project delay)
Employ additional resources (increased cost)
Reduce the scope of the project (less delivered)
Use the project schedule to justify pursuing one of these options.

## Slide 28: Supporting Plans you may need
Human Resource Plan
Communication Plan
Change Management
Risk Management Plan

## Slide 29: Human Resource Plan
Identify by name, type of skill/role and responsibilities to carry out the project.
1
Put the start dates, the duration and the method you will use for obtaining them in the project plan
2
Verify resources are not overbooked
3

## Slide 30: Communication planning
Who needs which reports, how often, in what format and using what media?
How issues will be escalated and to whom?
Where are project documents stored and who has access ?
What new risks have surfaced?
What metrics will be used to ensure a quality solution completed ?

## Slide 31: Change management
Processes, tools and techniques methodologies applied to changes of resources, business processes, budget allocations and other operational aspects of a project to achieve the required business outcome.

## Slide 32: Change Management Planning
Not all new requests will result in changes to the scope, schedule or budget, but a process is needed to evaluate all new requests to determine their impact on the project.
Different approval levels are often needed for different types of changes.

## Slide 33: Risk Management concerns
Time and cost estimate too optimistic
Customer review and feedback cycle too slow
Unexpected budget cuts
Unclear roles and responsibilities
Missing stakeholder input
Not clearly understanding stakeholder needs
Stakeholders changing requirements after the project has started

## Slide 34: List assumptions and risks
What are the known risks?
  Determine level of risk
  A stakeholder may provide information to eliminate or clarify the level of risk
Every assumption is a risk
  List them to make them visible to all stakeholders
  A stakeholder may provide information to eliminate or clarify the level of risk

## Slide 35: Risk Management concerns, continued
Stakeholders adding new requirements after the project has started
Poor communication resulting in quality problems and rework
Lack of resource commitment
Track risks using a risk log.
Process needed to mitigate risks.
Review of risk log on a regular basis.
Remember, if you ignore risks, they don't go away.

## Slide 36: Risk management
Every assumption is a potential risk.
Anticipate ways to mitigate risks with stakeholders.
Track risks using a risk log.
Review your risk log on a regular basis.
Remember, if you ignore risks, they don't go away.

## Slide 37: Congratulations!
Follow all the steps above, & you should have a good project plan.
Don't forget to update your plan as the project progress,
Keep measuring progress against the plan.

## Slide 38: Communicate plan to stakeholders
Review project plan with key stakeholders regularly.
Make changes as needed

## Slide 39: common problem
The sponsor imposes a delivery deadline that is not realistic based on your estimates.
The options you have in this situation are:
Renegotiate the deadline (project delay)
Employ additional resources (increased cost)
Reduce the scope of the project (less delivered)
Use the project schedule to justify pursuing one of these options.

## Slide 40: recap: Develop project plan
Use WBS to define required tasks
Estimate how many hours it each task/subtask will take to complete
Estimate cost of each task
Allocate resources to tasks. Ensure that correct resources are available
Determine critical path – this needs the project plan
Develop schedule, which puts all tasks and estimates in a calendar.

## Slide 41: Remember!
Developing a clear project plan takes time and input from all stakeholders.
The project manager should never be tempted to skip planning and jump straight into execution.