Affordable Learning Georgia Textbook Transformation Grants

Final Report for Mini-Grants

# General Information

Date: 8/14/22020

Grant Round: 15

Grant Number: M101

Institution Name(s): Georgia Gwinnett College

Team Members (Name, Title, Department, Institutions if different, and email address for each): Joycelyn Streator, PhD

Project Lead: Joycelyn Streator

Course Name(s) and Course Numbers: ITEC 2110 Digital Media

Final Semester of Project: Summer 2020

If applicable to your project:

Average Number of Students Per Course Section: 25/course

Number of Course Sections Affected by Implementation of Revised Resources: 51

Total Number of Students Affected by Implementation of Revised Resources: 1275

# Project Narrative

This project builds on the previous work by creating an updated workbook of connected learning activities and teaching strategies. These activities create a scaffolded learning environment;  the activities for one topic build on knowledge from the preceding topics. The workbook can work seamlessly with Dr. Lai and Chen’s works, providing additional hands-on training for ITEC 2110 students and faculty.

The project was created in three phases.  In the first phase (Fall 2020), media-rich activities were developed for the course, the framework for the Instructor’s Guide was created, and an IRB application for research was approved.  In phase 2, (SPRING 2020), the activities were piloted in one section of the course.  In phase 3 (Summer 2020), the pilot's results were incorporated into a final set of activities that were deployed to 1 section of ITEC 2110.  The original plan was to deploy the activities to more sections. However, the CoVID-19 Pandemic created major disruptions in planned pedagogy as all sections of the course were suddenly forced online.

After the project's conclusion, the Instructor's Guide and all activities were published at https://www.digital-research.org/digital-media-workbook.html.  The Digital Media Workbook is now available to all sections of ITEC 2110.

# Materials Description

The Digital Media Workbook

The Digital Media Workbook provides media-rich review questions for fundamental digital media concepts.  It’s recommended that students use the Interactive Workbook to review concepts from lectures or readings and assess their mastery.

The Digital Media Workbook Instructor’s Guide

The Instructor's Guide provides information on how to access and use the Digital Media Workbook.  It includes a suggested list of topics, along with concepts and skills for each topic.  The Guide also includes a list of free digital media resources.

# Materials Links

https://www.digital-research.org/digital-media-workbook.html

# Future Plans

Further plans include additional research on the use of scaffolding learning in asynchronous learning environments.  Data collection will continue through the AY 2020-21.

The web-based format of the Digital Media Workbook will allow for ongoing assessment of the Workbook features and continuous improvement.