Affordable Learning Georgia Textbook Transformation Grants

Final Report for Mini-Grants

# General Information

Date: May 12, 2021

Grant Round: 16

Grant Number: M110

Institution Name(s): University of North Georgia Oconee

Team Members (Name, Title, Department, Institutions if different, and email address for each):

Tashia Caughran, Senior Lecturer, tashia.caughran@ung.edu

Dr. Jeremy Cooper, Associate Professor, Jeremy.cooper@ung.edu

Dr. Jim Konzelman, Professor, jim.konzelman@ung.edu

Dan Sexton, Lecturer, dan.sexton@ung.edu

Project Lead: Tashia Caughran

Course Name(s) and Course Numbers: CHEM 2734 and CHEM 2734L

Final Semester of Project: Spring 2021

If applicable to your project:

Average Number of Students Per Course Section: None because our course was cancelled due to COVID

Number of Course Sections Affected by Implementation of Revised Resources: None because our course was cancelled due to COVID

Total Number of Students Affected by Implementation of Revised Resources: None because our course was cancelled due to COVID

# Project Narrative

Project Narrative

As a society, we are surrounded daily by numbers, data, and statistics.  These numbers provide important information.  However, they usually don’t show the entire picture of the data set gathered.  As scientists, it is of utmost importance that we not only gather data, but we understand what this data represents.  By understanding the entire picture, much more meaningful information can be shared.   In his book Innumeracy John Allen Paulos discusses how data can often be misrepresented to sway consumer or public opinion.  As scientists, it is vitally important that we represent data correctly and pass along this information in an ethical manner.

Students taking an Analytical chemistry course learn proper methods to gather data, statistically analyze the data, and discuss the meaning of the results and draw scientific conclusions.  The students develop critical thinking and analytical reasoning skills.  Many of the methods taught in the course are used in industry and government labs to ensure quality control, environmental regulation, criminal forensics, and food and drug regulations.

Our team was scheduled to teach an Analytical chemistry course in the spring of 2021.  While looking for course materials we realized the deficiency of materials available.  At the time of the grant proposal almost no open access resources were available for this course.  The proposal for this grant was to develop laboratory experiments to be used in the CHEM 2734 Lecture and lab course on the UNG Oconee campus.  The goal of our team was to offer a set of experiments in the open access format that can be used by any college or university offering an analytical course.  The experiments written for the grant include the following:  Activity and the Equilibrium Constant, Gravimetric Analysis, The Importance of Sampling, Preparation and Standardization of Acids and Bases, Statistics with an Excel ™ primer, Titration of an Acid, and Quantitative Analysis of Food Dyes using UV-VIS Spectrophotometry.

Project Plans and Timeline

All team members were involved in each of the tasks listed below:

May 1-10, 2020 Team members met to decide which topics would be chosen for the project

May 10, 2020-August 21, 2020 Outlines of the labs were written and discussed between team members.  Needed supplies were ordered to work with students on lab development

August 21, 2020-April 30, 2021 Lab procedures and content were developed during this time.  An undergraduate research student assisted with running trials of the UV-VIS lab.  Unfortunately, our Analytical course was cancelled due to COVID.  We were unable to perform trials of most of our experiments with students.  Therefore, were also not able to assess the labs with the original intention of the grant.

May 1, 2021-May 10, 2021 Written experiments were shared between team members and final edits were made.

Lessons Learned

Grant M110 was my third ALG grant project.  This grant presented a different set of challenges.  Our biggest challenge was the cancellation of the Analytical Chemistry course.  The grant was written specifically to write materials for this course.  Writing the material was difficult without the opportunity for assessment.  Edits for the labs will need to be made once assessment becomes possible.

I also found these items challenging during the course of our project

- I was surprised by the amount of paperwork for a grant within our institution.

- I struggled with the process to “zero out” my grant balance.

- I would have held more meetings within the team to tighten deadlines.

- Two of our team members became sick with COVID-19 during the last semester of the project.  The project felt somewhat rushed near the deadline.

# Materials Description

Seven laboratory exercises were developed for this grant.  A few of the experiments have been written in multiple parts.  Traditionally analytical chemistry courses include a large lab component in the curriculum.  The lab portion of the course may meet more than once a week.  Our team wrote these exercises to allow flexibility for their use depending on the course curriculum for a given university.  A brief discussion of each experiment is as follows:

Activity and the Equilibrium Constant-In this exercise, students will measure the effect of ionic strength on chemical equilibrium.  Students will use spreadsheet software to analyze absorption data and determine concentration of ionic species in solution, ionic strength, activity coefficients, and the value of an equilibrium constant.  To make these measurements, students will use UV-VIS spectroscopy to take absorbance measurements of an iron (III) thiocyanate complex ion.

Gravimetric Analysis- This exercise is written in three parts.  Gravimetric analysis is the process of determining the amount of a substance by mass. In part one, the amount of water contained in the salt, calcium carbonate will be determined by precipitation gravimetric analysis.  In part two students design and execute their own analysis of an eggshell to quantify the amount of calcium carbonate present using precipitation gravimetric analysis.  In part three, students will use a thermogravimetric technique to determine the calcium carbonate in an eggshell.  The precipitation and thermogravimetric techniques will be compared by statistical analysis.

Importance of Sampling- This exercise is written in two parts.  In part one students will count the number of copper and silver colored BBs in a heterogeneous sample.  This exercise teaches students to observe statistical fluctuations in a heterogeneous sample based on sample size, ratio, and distribution of particles in a sample.  In part two, students will calculate the spectrophotometric concentration and dry weight percent of potassium ferricyanide in a binary mixture with potassium chloride.  Students will evaluate the uncertainty of the analytical technique (error of the spectrophotometric measurements) using a standard ferricyanide solution of known concentration.  They will also calculate the error in the sampling method by investigating two samples of ferricyanide with different mesh sizes of particles.

Preparation and Standardization of Acids and Bases- In this exercise students will learn to prepare and standardize acids and bases for use in chemical titrations.  As a discipline, Analytical chemistry is concerned with the accuracy of results.  Therefore, it is important to know the exact concentrations of solutions to use in titrations and other analysis.  Students will use the primary standard potassium hydrogen phthalate to standardize a solution of sodium hydroxide and tris(hydroxymethyl)aminomethane to standardize a solution of hydrochloric acid.  The standardized acid and base solutions will be used in later lab exercises.

Statistics with an Excel™ primer- This exercise is written in two parts.  In the first part students will learn to use functions in Excel™ to perform statistical analysis on a large data set (500 pennies).  Part one includes specific instructions to introduce students to Excel™.  For the second part of the experiment, students will gather their own data using Fun Sized packages of M&Ms.  Students will then use Excel™ to analyze the meaning of the data gathered.  The focus of the statistical analysis will be to calculate averages, standard deviations, and medians for a large data set.  Students will also learn why those calculations are necessary and what those numbers ascertain about the data.

Titration of an Acid- Titrations are an important method used to accurately determine the quantity of chemical substance in a solution of unknown concentration.  This experiment will focus on the analysis of technical grade oxalic acid (C2O4H2, or (CO2H)2).  Students will prepare and titrate solutions of oxalic acid.  Techniques for determining the end point of the titration will include a visual technique (color change) using an indicator and a pH measurement.  Calculations will include determining the mass and percent by mass of oxalic acid along with average and standard deviation calculations for the titration trials.

Quantitative Analysis of Food Dyes using UV-VIS Spectrophotometry- In this experiment students will quantify the concentration of natural and artificial blue food dye in commercial food products.  Students will learn to make a series of solutions from standards of known concentrations of phycocyanin and FD&C Blue 1.  From this set of standard solutions, students will construct calibration curves for each dye.  Students will use UV-VIS spectrophotometry to determine the absorbance values of each solution.  They will then apply Beer’s Law to quantify the concentration of blue dye in some commercial products which use phycocyanin and FD&C Blue 1.

# Materials Links

Our materials will be available in the Galileo Open Access area.

# Future Plans

A poster presentation is planned for the fall ACS meeting in Atlanta, GA during the week of August 22, 2021.  An undergraduate student worked with Tashia Caughran on the development of the UV-VIS laboratory exercise.  The undergraduate was funded through a first-generation scholarship.

As a team we hope to teach the analytical course once full face to face courses can resume at our university.  During that time, we will be able to evaluate the laboratory exercises and make the necessary edits to improve them.  We also hope to write more labs for the course after the first set of experiments has been vetted.